## MMIXMv4.0.0 Change Requests
Release ID | Release | Summary | Description | Proposed Changes | Priority | Scale | Expected Impact to Implementers | Required Release | Disposition | Implementation Notes
MMIXMCR-58 | MMIXM v4.0.0 Beta | Add Provenance Data Type | Adding a new provenance data type consistent with the FIXM implementation of the provenance to add meta data about the source of the data represented in the model. | The proposed changes are: - adding Provenance as a new data type in MMIXMDataTypes - mapping new element to the new data type "Provenance" Include the following attributes: date: datetime type source: string type | High | Medium | None | Minor | Approved
MMIXMCR-59 | MMIXM v4.0.0 Beta | Create the Documentation Data Type | Create the Documentation Class to contain information regarding reference materials. | Create a Documentation Class in MMIXMDataTypes schema. Add the following attributes: identifier: string type changeNumber: String5Type type section: string type detail: String4000Type type Create the String4000Type to accommodate text contents. | High | Medium | None | Minor | Approved (With Modifications) | Rename changeNumber to revision before the final release In MMIXMCR-90 the decision was made to instead rename changeNumber to version
MMIXMCR-60 | MMIXM v4.0.0 Beta | Create the CodeDescriptionType Data Type | Create a common data type which allows publishers to support data with complex lookup tables, presented as a code and a text description of the code value. | Create a CodeDescriptionType Class in the MMIXMDataTypes schema. Add the following attributes: code: string type description: String4000Type type | High | Medium | None | Minor | Approved (With Modifications) | Verify String4000Type is needed before final, otherwise reduce length of description attribute. We did verify that String4000Type was still needed by a subset of attributes, but in MMIXMCR-91 the decision was made to change the description attribute from the String4000Type datatype to the String1000Type datatype
MMIXMCR-61 | MMIXM v4.0.0 Beta | Asset type to distinguish between facilities and equipment assets | Add AssetType to the Asset Class. | Modify the Asset Class to include the optional assetType attribute of type AssetType, with enumerated values of Assembly, Component, Equipment, Facility, lru, LRU, Module, Other, Part, Service, Subassembly, Subsystem, System | High | Medium | None | Minor | Approved
MMIXMCR-62 | MMIXM v4.0.0 Beta | Changes for consistent handling of Locations | Address all changes related to the FAA related locations, building, and contents there of the building including types of locations with details related to that location. | Modify the Location type to accommodate additional details: Location.PhysicalAddress.buildYear: string type Location.PhysicalAddress.estimatedTravelDuration: duration type Location.PhysicalAddress.estimatedTrips: integer type Location.GeographicLocation.geographicLocationProvenance: Provenance type Expand CodeFaaLocationType enumeration to accommodate common facility types in FSEP data - Add: ATCT, ATCSCC, CERAP Add attributes to the FsepOpearationalInformation Class, all of type Location: airTrafficLocation: Location type buildingLocation: Location type commandLocation: Location type controlLocation: Location type monitorLocation: Location type primaryLocation: Location type remoteLocation: Location type serviceDeliveryPointLocation: Location type | High | Medium | Medium | Minor | Approved (With Modifications) | Verify type information after beta release. See MMIXMCR-95
MMIXMCR-63 | MMIXM v4.0.0 Beta | Refine runway and airport information | Allow identification of runways using the "X" suffix. | Modify the RunwayType constraint to allow runways using the "X" identifying letter. | High | Small | None | Patch | Approved
MMIXMCR-64 | MMIXM v4.0.0 Beta | Expand Routing Code information | Adding routing code hierarchy information to include organization names, and add previous routing code. | Add attributes to the AtowOrganization Class: serviceAreaName: string type districtOfficeName: string type groupName: string type sscName: string type previousAtowCode: AtowCodeType type atowCodeChangeProvenance: Provenance type Revise AtowCodeType to allow alphanumeric values in the third character | High | Small | None | Minor | Approved (With Modifications) | Revisit ordering of attributes before final. Attribute sequence tags were reviewed after the determination made was made to revert back to model group: sequence. See the Implementation Notes column for MMIXMCR-85 for more details.
MMIXMCR-65 | MMIXM v4.0.0 Beta | Accommodate changes to FSEP Information | Address changes related to FSEP information details. | Add the following attributes to the FsepOperationalInformation Class: assetStatusHistory.assetStatus: CodeDescriptionType type previousRegionCode: CodeRegionType type frequencyCount: integer type regionalInformation: String15Type type with integer attribute called "id", limit multiplicity to [0..3] recordProvenance: Provenance type fsepCode.fsepCodeClassDescription: string type fsepCode.powerCode: string type fsepCode.restorationCode: String5Type type Add the following attributes to the AssetIdentifier Class: previousFsepLocId: FsepLocIdType type previousFsepFac: FsepFacType type | High | Medium | None | Minor | Approved (With Modifications) | Revisit orphaned datatypes after Beta. See MMIXMCR-83 & MMIXMCR-87
MMIXMCR-66 | MMIXM v4.0.0 Beta | Create the Logging package | Create Logging package, diagrams, and attributes to support log-related information. | Create Logging package to include all classes and features as necessary for accommodating logging information additions. Update diagrams and associations as necessary. | High | Large | None | Minor | Approved
MMIXMCR-67 | MMIXM v4.0.0 Beta | Create the LoggingEvent Class | Create a Class to contain Log and log-related information. | Create the LoggingEvent Class as an attribute of the Asset Class. Add the following attributes: additionalInformation: AdditionalInformation type comment: string4000Type type createdBy: ContactInformation type createdDateTime: datetime type creatorLocation: Location type logId: integer22Type type modifiedBy: Contactinformation type modifiedDateTime: datetimeTime reportLevel: String1Type type status: CodeLogStatusDescriptionType type, Add the CodeLogStatusDescriptionType enumerated type to MMIXMDataTypes, values of OPEN, CLOSED, VOID summary: string255Type type, create string255Type | High | Medium | None | Minor | Approved
MMIXMCR-68 | MMIXM v4.0.0 Beta | Create the ArrivalDeparture Class | Create the ArrivalDeparture Class to contain arrival and departure log information. | Add the ArrivalDeparture Class as an attribute of LoggingEvent. Add the following attributes: arrivalDateTime: datetime type departureDateTime : datetime type actualTravelDuration: duration type | High | Medium | None | Minor | Approved
MMIXMCR-69 | MMIXM v4.0.0 Beta | Create the AssignmentInformation Class | Create the AssignmentInformation Class to contain assignment information. | Create the AssignmentInformation Class as an attribute of the LoggingEvent Class Add the following attributes: assignedGroup: string type assignedSpecialist: ContactInformation type | High | Medium | None | Minor | Approved
MMIXMCR-70 | MMIXM v4.0.0 Beta | Support Logging Coordination | Create the LogCoordination Class. | Create the LogCoordination Class as an attribute of the LoggingEvent Class. Add the following attributes: electronicFlag: Boolean type coordinationFlag: Boolean type coordinationStage: CodeCoordinationRestStageDescriptionType type, add CodeCoordinationRestStageDescriptionType enumerated type with values below. CodeCoordinationRestStageDescriptionType values: APPROVED, CALLBACK ACCEPTED, CANCELLED, DEFERRED, DELAYED, DISAPPROVED, NOT COORDINATED, PENDING APPROVAL, PENDING NOTIFICATION, RETURNED TO SERVICE, ERTS_REQUEST | High | Medium | None | Minor | Approved
MMIXMCR-71 | MMIXM v4.0.0 Beta | Create the LoggingCode Class | Create the LoggingCode Class to contain codes associated with log entries. | Add the LoggingCode Class as an attribute of LoggingEvent Class. Add the following attributes: maintenanceAction: CodeDescription type category: CodeDescription type supplemental: CodeDescription type | High | Medium | None | Minor | Approved (With Modifications) | Revisit categoryCode in FsepOperationalInformation to ensure elements are not duplicated. MMIXMCR-87 removed categoryCode from Asset.FsepOperationalInformation
MMIXMCR-72 | MMIXM v4.0.0 Beta | Create the MaintenanceActivity Class | Create the MaintenanceActivity Class to support logging of activity begin and end dates. | Create the MaintenanceActivity Class as an attribute of LoggingEvent Class. Add the following attributes: activityStartDateTime: datetime type activityEndDateTime: datetime type | High | Medium | None | Minor | Approved
MMIXMCR-73 | MMIXM v4.0.0 Beta | Create the NotamInformation Class | Support NOTAMs referenced in log entries. | Create the NotamInformation Class as an attribute of LoggingEvent Class. Add the following attributes: transactionId: int type | High | Medium | None | Minor | Approved
MMIXMCR-74 | MMIXM v4.0.0 Beta | Create the Alarm Class | Create the Alarm Class. | Create the Alarm XSDComplexType as an attribute of the LoggingEvent Class. Add the following attributes: alarmInformation: MonitoringEvent type, expand RmlsConditionCodeType to accommodate PSEUDO_FLAG values inputParameter, string type remoteAction: string type remoteResponse: CodeDescription type RmlsConditionCodeType values: A: Alarm C: State Change I: Invisible L: Warning R: Return to Normal S: Site Data Report -- retain other existing values: N: Indicates that a RMLS Data Point is in an active, unacknowledged, alarm state. P: Indicates that a RMLS Data Point is in an active, unacknowledged, alert/warning state. | High | Medium | None | Minor | Approved (With Modifications) | After the beta release, revisit definitions to RmlsConditionCodeType to ensure consistent definitions. See MMIXMCR-100 for resolution
MMIXMCR-75 | MMIXM v4.0.0 Beta | Create the InterruptReport Class | Create the InterruptReport Class to accommodate interrupt reporting. | Create the InterruptReport Class as an attribute of the LoggingEvent Class. Add the following attributes to the InterruptReport XSDComplexTtype: acknowledgedBy: ContactInformation type acknowledgedDateTime: datetime type acknowledgedFlag: Boolean type airTrafficImpact: AirTrafficImpactType type, create AirTrafficImpactType enumerated field in MMIXMDataTypes with values "none, low, moderate, high" continuityOfService: continuityOfServiceType type, add a new enumeration in the MMIXMDataTypes called "continuityOfServiceType" values of 0,1,2,null deviceProvenance: Provenance type estimatedRepairDuration, Duration type eventType: CodeDescription type failureInformation: CodeDescriptionType followUpDateTime: datetime impactLevel: CodeDescriptionType independentEditFlag: Boolean type interruptType: CodeInterruptConditionDescriptionType type, add CodeInterruptConditionDescriptionType enumeration in the MMIXMDataTypes, values of "FULL INTERRUPTION, INFORMATIONAL ENTRY, REDUCED FAC/SERV INTERRUPTION, REDUCED SYSTEM/EQUIPMENT", sourced from INTERRUPT_CONDITION operationalContingency: OperationalContingencyType type, add OperationalContingencyType enumerated type to MMIXMDataTypes with values ATC-Alert, ATC-Limited, ATC-Zero, Null pagedBackFlag: Boolean type pagedOutFlag: Boolean type pagedUpdateFlag: Boolean type primeRecovery: CodeDescription type remoteSaveFlag: Boolean type reviewedFlag: Boolean type uncheduledFlag: Boolean type | High | Medium | None | Minor | Approved (With Modifications) | After the beta release, revisit ContinuityOfServiceType values to see if they can be enumerated to readable values. Revisit Fault Location SWIM data See MMIXMCR-88
MMIXMCR-76 | MMIXM v4.0.0 Beta | Create the Cause Class as an attribute of InterruptReport | Create the Cause Class as an attribute of InterruptReport. | Create the Cause XSDcomplexType as an attribute of InterruptReport Add the following attributes: causeGroup: CodeDescription type causeSubgroup: CodeDescription type rawText: string type | High | Medium | None | Minor | Approved (With Modifications) | After beta release, revisit "group" naming convention throughout the model to make sure verbiage is consistent. See MMIXMCR-89
MMIXMCR-77 | MMIXM v4.0.0 Beta | Create the BackupStatus Class as an attribute of InterruptReport | Create the BackupStatus Class as an attribute of InterruptReport. | Create the BackupStatus XSDcomplexType as an attribute of InterruptReport Add the following attributes: backupCategory: string50 type backupStartDateTime: datetime type backupEndDateTime: datetime type backupInUseAsPrimary: Boolean type | High | Medium | None | Minor | Approved
MMIXMCR-78 | MMIXM v4.0.0 Beta | Create the PeriodicMaintenance Class | The goal of this CR to group all the remaining elements under PM that are not part of the common Values. | Add the PeriodicMaintenance Class as an attribute of the LoggingEvent Class Add the following attributes to the PeriodicMaintenance Class: assignmentNumber: integer description: String4000Type earliestDateTime: dateTime latestDateTime: dateTime groupClosureCode: String10Type type publication: Documentation type scheduleDateTime: dateTime schedulingCode: String1Type type unitTag: string type | High | Medium | None | Minor | Approved (With Modifications) | After beta release, revisit overall MMIXM guidance/vision, regarding in particular naming convention of specific elements like "Assignment Number" vs. more generalized "Task Identifier", to balance between supporting existing terminology and supporting the conceptual structure of the data
MMIXMCR-79 | MMIXM v4.0.0 Beta | Create the AssetCertification Class as an attribute of PeriodicMaintenance | Create the AssetCertification Class as an attribute of PeriodicMaintenance. | Create AssetCertification Class as an attribute of PeriodicMaintenance Add the following attributes: interval: CodeDescription type statement: CodeDescription type | High | Medium | None | Minor | Approved (With Modifications) | After beta release, revisit naming of Certification Classes: Personnel vs. Asset
MMIXMCR-80 | MMIXM v4.0.0 Beta | Create the Task Class as an attribute of PeriodicMaintenance | Create the Task Class as an attribute of PeriodicMaintenance. | Create Task Class as an attribute of PeriodicMaintenance Class Add the following attributes: interval: CodeDescriptionType glossary: CodeDescriptionType numberOfTasks: nonNegativeInteger type | High | Medium | None | Minor | Approved
MMIXMCR-81 | MMIXM v4.0.0 Beta | Create the EquipmentMaintenance Class | Create the EquipmentMaintenance Class and make other modifications to support Equipment logging. | Add the EquipmentMaintenance Class as an attribute of LoggingEvent Class Add the following attributes to the EquipmentMaintenance Class: changeNumber: String10Type type directiveLevel: CodeDescriptionType modification: Documentation type modificationType: CodeDescriptionType projectCode: string type Modify AssetIdentifier.ManufacturerIdentifier.revisionNumber to String50Type | High | Medium | None | Minor | Approved (With Modifications) | After beta release, revisit alignment of our nomenclature for “types”, “categories”, “groups”, and “class”. See MMIXMCR-89 & MMIXMCR-90
MMIXMCR-82 | MMIXM v4.0.0 Beta | Create the AssetOrder Class | Create the AssetOrder Class. | Create the AssetOrder XSDComplexType as an attribute of EquipmentMaintenance Add the following attributes: assetOrderDateTime: dateTime type assetReceiptDateTime: dateTime type assetOrderRequired: CodeDescription type trackingNumber: String15Type type | High | Medium | None | Minor | Approved
MMIXMCR-83 | MMIXM v4.0.0 Beta | Cleaning deprecated or inconsistent elements | Perform cleanup actions resulting from Location and Provenance updates. | Cleanup items for consistency: Remove the 'source' attribute from Location.GeographicLocation Modify FsepOperationalInformation.coreAirport attribute to Location type for consistency with other location data elements Remove assetStatusHistory.assetStatusCode Remove CodeAssetStatusType enumeration | Low | Small | None | Major | Approved (With Modifications) | Revisit cleanup items after beta release. Expect to indicate in the definitions that these fields are to be deprecated or updated in a future release.
MMIXMCR-84 | MMIXM v4.0.0 Beta | Update staffedHours attribute type | Revise staffedHours to accommodate text. | Change FsepOperationalInformation.staffedHours to xs:string | High | Small | None | Patch | Approved
MMIXMCR-85 | MMIXM v4.0.0 RC | Change the model group of the entire model | Change the model group from "sequence" to "all" for the entire logical model. | Change each instance of Model Group "Sequence" to Model Group "All" for the entire schema. If the model group is set to "choice" do not change the model group. The model groups of the XSDcomplexTypes FaaLocationTypeChoice and QualificationChoice will not be changing | High | Large | None | Patch | Disapproved (With Modifications) | Model group reverted to "Sequence" due to stakeholder implementation difficulties using XSD v1.1 validation. Converting the model group to "All" and subsequently implementing XSD v1.1 will be revisted in a later update.
MMIXMCR-86 | MMIXM v4.0.0 RC | Create new XSDsimpleType in MMIXMDataTypes | Create XSDsimpleTypes in the MMIXMDataTypes schema. | Create String1000Type in MMIXMDataTypes Set the definition to: "Specifies a string of up to 1000 characters." Create String150Type in MMIXMDataTypes Set the definition to: "Specifies a string of up to 150 characters." Create TextCountryCodeType in MMIXMDataTypes Set the pattern restriction to [A-Z]{2} Set the definition to: "The country code as specified by ISO 3166." Create TextCountryNameType in MMIXMDataTypes Set the data type to xs:string Set the minLength to 0, and maxLength to 60 Set the definition to: "The country of the physical address for the location or organization. Full name, not ISO 3166 abbreviations. [AIXM 5.1]" | High | Small | None | Patch | Approved
MMIXMCR-87 | MMIXM v4.0.0 RC | Delete attributes and datatypes | Delete attributes and datatypes that are no longer in use. | Delete the categoryCode attribute from Asset.FsepOperationalInformation Delete the CodeCategoryType enumeration from MMIXMDataTypes Delete the XSDsimpleType AirportCodeType from MMIXMDataTypes Delete the attribute fsepCodeClassDescription from Asset.FsepOperationalInformation.FsepCode Delete the CodeFsepClassType enumeration from MMIXMDataTypes Delete the attribute numberOfTasks from LoggingEvent.PeriodicMaintenance.Task | High | Small | None | Major | Approved
MMIXMCR-88 | MMIXM v4.0.0 RC | Adjust enumeration values | Adjust the enumeration values for the ContinuityOfServiceType & OperationalContingencyType data types. | Change the enumeration values of ContinuityOfServiceType from 0, 1, 2, & Null to false, true, reserved. Drop the null value from both ContinuityOfServiceType & OperationalContingencyType Change the value "AIRPORT" to "Airport" in the enumeration CodeFaaLocationType | High | Small | None | Patch | Approved
MMIXMCR-89 | MMIXM v4.0.0 RC | Changes to prefixes | Remove prefixes from the attribute names of several attributes. | Change addressCategory to category in the ContactInformation.PostalAddress XSDcomplexType Change faaLocationIdentifier to identifier in the Location.FaaLocation XSDcomplexType Change faaLocationType to type in the Location.FaaLocation XSDcomplexType Change alarmInformation to information in the LoggingEvent.Alarm XSDcomplexType Change assetOrderDateTime to dateTime in the LoggingEvent.EquipmentMaintenance.AssetOrder XSDcomplexType Change assetOrderRequired to required in the LoggingEvent.EquipmentMaintenance.AssetOrder XSDcomplexType Change causeGroup to group in the LoggingEvent.InterruptReport.Cause XSDcomplexType Change causeSubgroup to subgroup in the LoggingEvent.InterruptReport.Cause XSDcomplexType Change certificationStatus to status in the Qualification.QualificationChoice.Certification XSDcomplexType Change certificationType to type in the Qualification.QualificationChoice.Certification XSDcomplexType | High | Medium | None | Major | Approved
MMIXMCR-90 | MMIXM v4.0.0 RC | Attribute name changes | Adjust the names of attributes and make corrections previously missed from MMIXMCR-71. | Change changeNumber to version in the Documentation XSDcomplexType in MMIXMDatatypes Correcting codeCategory to category in LoggingEvent.LoggingCode XSDcomplexType Correcting maintenanceActionCode to maintenanceAction in LoggingEvent.LoggingCode XSDcomplexType Correcting supplementalCode to supplemental in LoggingEvent.LoggingCode XSDcomplexType Change fsepClassCode to fsepClass in Asset.FsepOperationalInformation.FsepCode Change restorationCode to restorationPeriod in Asset.FsepOperationalInformation.FsepCode | High | Small | None | Patch | Approved
MMIXMCR-91 | MMIXM v4.0.0 RC | Adjust datatypes | Adjust the datatypes of certain attributes to better fit sample data. | Change the datatypes of attributes: In the ContactInformation schema: email from xs:string to String255Type category from xs:string to String15Type administrativeArea from xs:string to UsStateAbbreviationType city from xs:string to String50Type countryCode from xs:string to TextCountryCodeType countryName from xs:string to TextCountryNameType deliveryPoint from xs:string to String255Type phoneCategory from xs:string to String15Type In the Location schema: ip from xs:string to String50Type textDescription from xs:string to String255Type buildYear from xs:string to YearType description from xs:string to String255Type faaLocationIdentifier from xs:string to String5Type In the Message schema: collectionType from xs:string to String50Type id from xs:string to String50Type (Both id's in Message & MessageCollection) messageType from xs:string to String50Type In the MMIXMDataTypes schema: CodeDescriptionType.code from xs:string to String10Type CodeDescriptionType.description from String4000Type to String1000Type Documentation.identifier from xs:string to String50Type Documentation.section from xs:string to String10Type locationOtherType from xs:string to String15Type Provenance.source from xs:string to String50Type In the PersonOrganization schema: firstName from xs:string to String50Type lastName from xs:string to String50Type middleName from xs:string to String50Type suffix from xs:string to String10Type title from xs:string to String50Type organizationName from xs:string to String150Type districtOfficeName from xs:string to String150Type groupName from xs:string to String150Type serviceAreaName from xs:string to String150Type sscName from xs:string to String150Type In the Asset schema: assetName from xs:string to String150Type description from xs:string to String255Type staffedHours from xs:string to CodeDescriptionType powerCode from xs:string to String1Type fsepClass from CodeFsepClassType to CodeDescriptionType restorationPeriod from String5Type to CodeDescriptionType id from regionalInformationType from integer to String1Type In the Asset Identifier schema: facaNumber from xs:string to String50Type In the Logging schema: assignedGroup from xs:string to String50Type inputParameter from xs:string to String10Type remoteAction from xs:string to String50Type rawText from xs:string to String50Type unitTag from xs:integer to String10Type projectCode from xs:string to String10Type In the Monitoring schema: eventDescription from xs:string to String255Type eventTitle from xs:string to String50Type violation from xs:string to String50Type violationUserName from xs:string to String255Type Parameter.name from xs:string to String150Type Configuration.name from xs:string to String150Type currentValue from xs:string to String50Type previousValue from xs:string to String50Type | High | Large | None | Patch | Approved
MMIXMCR-92 | MMIXM v4.0.0 RC | Add missing XSDcomplexTypes to diagrams | Add missing XSDcomplexTypes to diagrams. | Add the XSDcomplexTypes AdditionalInformation and NameValuePair to the Message diagram Add the XSDcomplexTypes RegionalInformationType, RunwayInformation, and Provenance to the Asset diagram Add the XSDcomplexTypes CodeDescriptionType and Documentation to the Logging diagram | High | Small | None | Patch | Approved
MMIXMCR-93 | MMIXM v4.0.0 RC | Delete XSD Class from schema | Delete the FsepIdentifier linked XSDcomplexType and the associated relationship from the Logging schema. | Delete the XSDcomplexType FsepIdentifier from the Logging schema Delete the associated relationship from the Logging schema as well | High | Small | None | Minor | Approved
MMIXMCR-94 | MMIXM v4.0.0 RC | Add attributes to the schema | Add a trigger attribute to the Message schema. Add a FSEP operational information snapshot to the Logging schema. Add a FSEP reference ID to the Asset Identifier schema. Add numberOfTasksEstimated & numberOfTasksActual to the Logging schema. | Add trigger as an attribute to the Message XSDcomplexType Set the datatype to String50Type Add fsepOperationalInformationSnapshot as an attribute to the LoggingEvent XSDcomplexType Set the datatype to FsepOperationalInformation Add numberOfTasksEstimated as an attribute to the Task XSDcomplexType Set the datatype to nonNegativeInteger Add numberOfTasksActual as an attribute to the Task XSDcomplexType Set the datatype to nonNegativeInteger Add fsepReferenceId as an attribute to the FsepIdentifier XSDcomplexType in the AssetIdentifier schema Set the datatype to xs:integer | High | Small | None | Minor | Approved
MMIXMCR-95 | MMIXM v4.0.0 RC | Reorganize FSEP related attributes | Move all location based attributes from FsepOperationalInformation into a new XSDcomplexType and consolidate FSEP codes. | Move responsibilityCode and capabilityCode attributes from the FsepOperationalInformation XSDcomplexType into the FsepCode XSDcomplexType Create a new XSDcomplexType called AssociatedLocations in the Asset schema Create a link from FsepOperationalInformation to the new XSDcomplexType Move the attributes airTrafficLocation, buildingLocation, commandLocation, controlLocation, monitorLocation, previousRegionCode, primaryLocation, regionCode, remoteLocation, and serviceDeliveryPointLocation from the FsepOperationalInformation XSDcomplexType to the new AssociatedLocations XSDcomplexType | High | Medium | None | Major | Approved
MMIXMCR-96 | MMIXM v4.0.0 RC | Update definitions | Add and update definitions for new attributes, data types, enumeration values added to the schema since v3.0.0, as well as definitions requiring cleanup for accuracy and consistency. | Add and update definitions for attributes, data types, enumeration values, including those referenced in the following CRs: MMIXMCR-86, MMIXMCR-88, MMIXMCR-94. | High | Large | None | Minor | Approved
MMIXMCR-97 | MMIXM v4.0.0 RC | Rename equipmentMaintenance to equipmentModification | Rename equipmentMaintenance and update related fields for consistency. | Change EquipmentMaintenance XSDcomplexType name to EquipmentModification Change equipmentMaintenance element name to equipmentModification Update definitions to replace "equipment maintenance" with "equipment modification" | High | Small | None | Major | Approved
MMIXMCR-98 | MMIXM v4.0.0 Final | Change the relationship between Organization and AtowOrganization | Move away from the use of Generalization relationship to relate Organization and AtowOrganization, to reduce the need to specify the datatype when describing the responsible organization of an asset. | Change relationship between Organization and AtowOrganization from Generalization to a simple association, directed from Organization to AtowOrganization. Identify the role of the new association "atowOrganization", with a definition based the definition of AtowOrganization. | Low | Medium | Low | Major | Approved
MMIXMCR-99 | MMIXM v4.0.0 Final | Update Air Traffic Impact definitions | Provide specific examples of the various levels of Air Traffic Impact Type enumerated values. | Update definitions for the AirTrafficImpactType enumerated values: none: No impact to air traffic services, as defined in the appropriate facility SOP. low: Low or negligible impact to air traffic services, as defined in the appropriate facility SOP. For example, "low" may indicate less than 15 minutes of air traffic delay, or a Traffic Management Initiative (TMI) is unnecessary or possible. moderate: Moderate impact to air traffic services, as defined in the appropriate facility SOP. For example, "moderate" may indicate a 15 to 45 minute air traffic delay, or a Traffic Management Initiative (TMI) is implemented, or the event has local media interest. high: High or significant impact to air traffic services, as defined in the appropriate facility SOP. For example, "high" may indicate a greater than 45 minute air traffic delay, or a ground stop is implemented beyond an internal implementation, or the event has national media interest. | Low | Small | None | Patch | Approved
MMIXMCR-100 | MMIXM v4.0.0 Final | Convert attributes to elements in Convert RmlsDpInformation and HolderStatus | Convert the children of the RmlsDpInformation complex type from attributes to elements, to bring them more in line with the structure of the rest of the model. For HolderStatus, the desired implementation in 2023-06 MMIXM TIM was a complex type with a single qualifier attribute. This update completes that action item. | Remove the xsdAttribute stereotype from RmlsDpInformation.*. Convert HolderStatus to type CodeHolderStatusType. Remove HolderStatus.status attribute. | Low | Medium | Low | Major | Approved
MMIXMCR-101 | MMIXM v4.0.0 Final | Adjust attribute names | Adjust the names of attributes in the Asset, Logging, and PersonOrganization schema. | Adjust the attribute names: ndcEmpID to ndcEmpId in the Person XSDcomplexType in the PersonOrgranization schema revisionID to revisionId in the fsepOperationalInformation XSDcomplexType in the Asset schema | Low | Small | None | Major | Approved